## Communication Plan
Communication Plan
#REF!
Strategy Development
COMMUNICATION PLAN
TEMPLATE
| Communication Type | Communication Objective | Medium | Frequency | Audience | Owner | Deliverable | Format
EXAMPLE | Kick-Off Meeting | Introduce Project and Project Team. Review Project Scope and Objectives | Face to Face | Once | Project Sponsor, Project Team, Stakeholders | Project Manager | Agenda & Meeting Minutes | Soft Copy archived on Share Point Site
1 | Lean Awareness session | Invite all VSM participants for a brief overview of Lean Principles, with strong emphasis on VALUE & 8 types of waste | F2F Virtual Training | Once | VSM interviewees, their bosses if they are interested. | Lean Master | Introduction to the team, background / context to the initiative, light intro to VALUE & Waste | MS Teams
2 | Leadership Approval of SIPOC & Scope | Inform and obtain feedback from leadership team to get their "blessings" on moving forward with VSM. Also to initiate and plan communication to larger oragnization. | F2F?? | Once | Lean Master, Leadership stakeholders | Lean Master
3 | Initiative Updates
4 | VSM review with managers
5 | VSM Summary Report out to Leadership team
6
7
8
9
10
11
12