## Slide 1
Lean Six Sigma Project Charter
Title: Reduce Scrapped Cookies in NW Region BB/GB: B. Thornton
Business Gap
Defects & Metrics
Problem Statement
Team: B. Thornton (BB), A Yamoto (Process Owner), W. Houston (SME), P. Smith (SME), G. Hines (SME), L. David (SME)
Champion: T. Wong
Project Scope/Boundaries:
Process Start: Mix Ingredients
Process Stop: Bake Cookies
In Scope: Chocolate Chip Cookies in all NW Bakeries
Out of Scope: Packaging
Milestones/Timeline: Scheduled Actual
Define Tollgate Review: June 4, 2024 6-4-24
Measure Tollgate Review: July 9, 2024
Analyze Tollgate Review: August 13, 2024
Improve Tollgate Review: September 10, 2024
Control Tollgate Review: September 24, 2024
Customer
Objective Statement
Our bakeries scrap approximately 25% of all cookies baked. Scrapped cookies limit our ability to remain profitable while we are being pressured to reduce prices by our competitors. Scrapped cookies have always been an issue and it has become worse since new ovens were installed. Based on a Pareto Analysis we will focus initially on the NW Region.
External: Grocery Stores, Consumer
Internal: Regional General Manager
Defects: Scrapped Cookies
Primary: Scrap Rate for Cracked Chocolate Chip Cookies (CCCC)
Secondary: Returns dues to CCCC’s
Consequential: Taste, Chewiness
The scrap rate due to cracked chocolate chip cookies in the NW bakeries was 15% for the past 12 months based on daily scrap reports.
Reduce the scrap rate due to cracks from 15% to 8% by 11/12/24 as measured by the daily scrap report
Financial Impact
$204,400 in direct savings based on current production rates
© Lean Methods Group. Except as may be expressly authorized by a written license agreement signed by Lean Methods Group, no portion may be altered, rewritten, edited, modified or used to create any derivative works.

## Slide 2
Project Charter
Title: x BB/GB: x
Business Gap
Defects & Metrics
Problem Statement
Team: x
Champion: x
Project Scope/Boundaries:
Process Start: x
Process Stop: x
In Scope: x
Out of Scope: x
Milestones/Timeline: Scheduled Actual
Define Tollgate Review: x x
Measure Tollgate Review: x
Analyze Tollgate Review: x
Improve Tollgate Review: x
Control Tollgate Review: x
Customer
Objective Statement
x
External: x
Internal: x
Defects: x
Primary: x
Secondary: x
Consequential: x
x
x
Financial Impact
$x