## Stakeholder Diagnostic
Stakeholder Diagnostic
Closed circle: stakeholder is KNOWN to offer this current support
Open circle: we think the stakeholder is offering this current support
| Key Stakeholder | Role in Organization | Power/ Influence Category | Impact of Program on Stakeholder (H, M, L) | Current/Desired Support |  |  |  |  | Reasons for Resistance or Support
[5 empty] | Strongly Opposed | Opposed | Neutral | Supportive | Strongly Supportive
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Stakeholder Diagnostic SAMPLE
| Key Stakeholder | Role in Organization | Power/ Influence Category | Impact of Project on Stakeholder (H, M, L) | Current/Desired Support |  |  |  |  | Reasons for Resistance or Support
[5 empty] | Strongly Opposed | Opposed | Neutral | Supportive | Strongly Supportive
1 | John Smith | Quality Manager | A | M | [5 empty] | T - Project will reduce most common defect.
2 | Mary James | VP Operations | C | M
3 | Susan Davis | Production Supervisor | A | H | [5 empty] | T - Resultant yield increase.
4 | David Kelly | Repair Tech | B | M | [5 empty] | P - Changes imposed by others.
5 | Mark Thomas | Quality Engineer | B | H | [5 empty] | P - Disagrees with priority of project relative to others.
6 | Terry Nolan | Quality Engineer | B | H | [5 empty] | T - Project will reduce most common defect.
7 | Wendy Ryan | Operator | B | H | [5 empty] | T - Job will be easier.
8 | Fred Granger | Inspector | D | H | [5 empty] | P - Fears job loss. C - Feels left out of decisions.
9 | Holly Lewis | Accounting Mgr | C | L
10
11
12
13
14
15
16
17
18
19
20

## Stakeholder Power Influence Map
Stakeholder Influence Map
| LOW | Influence Over Project | HIGH
HIGH
Power in Organization
LOW
C
A
D
B

## Power-Influence Map SAMPLE
| LOW | Influence Over Project |  |  |  |  | HIGH
HIGH
Power in Organization
Mary James
|  | Holly Lewis |  |  | John Smith
Susan Davis
Terry Nolan
Mark Thomas
Wendy Ryan
|  |  |  | Fred Granger | David Kelly
LOW
C
A
D
B

## Stakeholder Influence Matrix
Stakeholder Influence Matrix
Influential Stakeholder ▼ | Who They Influence
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | bar: Who They Influence 1
2 | bar: Who They Influence 2
3 | bar: Who They Influence 3
4 | bar: Who They Influence 4
5 | bar: Who They Influence 5
6 | bar: Who They Influence 6
7 | bar: Who They Influence 7
8 | bar: Who They Influence 8
9 | bar: Who They Influence 9
10 | bar: Who They Influence 10
11 | bar: Who They Influence 11
12 | bar: Who They Influence 12
13 | bar: Who They Influence 13
14 | bar: Who They Influence 14
15 | bar: Who They Influence 15
16 | bar: Who They Influence 16
17 | bar: Who They Influence 17
18 | bar: Who They Influence 18
19 | bar: Who They Influence 19
20 | bar: Who They Influence 20
Instructions:
Enter stakeholder names in column C. Each stakeholder has a number to the left of their name. Corresponding number appear across the top.
In matrix area, enter a lower case letter to indicate how strong the influence over another stakeholder. Use h for high, m for medium, and l for low.

## Influence Matrix SAMPLE
Influential Stakeholder ▼ |  | Who They Influence
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | John Smith | Who They Influence 1: X; Who They Influence 3: m; Who They Influence 4: l; Who They Influence 5: h; Who They Influence 6: h; Who They Influence 8: h
2 | Mary James | Who They Influence 1: h; Who They Influence 2: X; Who They Influence 3: h; Who They Influence 7: m; Who They Influence 9: h
3 | Susan Davis | Who They Influence 1: m; Who They Influence 3: X; Who They Influence 4: h; Who They Influence 7: h; Who They Influence 8: m
4 | David Kelly | bar: Who They Influence 4; Who They Influence 7
5 | Mark Thomas | Who They Influence 1: m; Who They Influence 5: X; Who They Influence 6: h; Who They Influence 8: h
6 | Terry Nolan | bar: Who They Influence 1; Who They Influence 5 to Who They Influence 6; Who They Influence 8
7 | Wendy Ryan | bar: Who They Influence 3; Who They Influence 7
8 | Fred Granger | bar: Who They Influence 8
9 | Holly Lewis | Who They Influence 2: m; Who They Influence 3: h; Who They Influence 9: X
10 | bar: Who They Influence 10
11 | bar: Who They Influence 11
12 | bar: Who They Influence 12
13 | bar: Who They Influence 13
14 | bar: Who They Influence 14
15 | bar: Who They Influence 15
Instructions:
Enter stakeholder names in column C. Each stakeholder has a number to the left of their name. Corresponding number appear across the top.
In matrix area, enter a lower case letter to indicate how strong the influence over another stakeholder. Use h for high, m for medium, and l for low.

## Resistance Dignosis
Stakeholder Name | John Smith
Specific Resistant Behaviors Observed
Early Signs of Resistance | Gossip or Testing
Reasons for Resistance | Parocial Self Interest, Misunderstanding, Low Tolerance for Change, Different Assessmentof the Situation
Activity of Resistance | Active or Passive
Visibility of Resistance | Overt or Covert
Collectivism of Resistance | Individual or Group
Strategy(s) to overcome the Resistance | Education & Communication, Participation & Involvement, Facilitation & Support, Negotiation & Agreement, Manipulation & Co-Option, Explicit & Implicit Coercion

## Stakeholder Action Plans
Stakeholder Action Plan
Rank | Stakeholder | Perceived DISC | Preferred method of Communication | Leverageable Allies | Advantages for this stakeholder (answer to: "What is in it for me?") | Reason for Resistance (if any) | Strategy to Overcome Resistance | Communication Tips and Reminders | Anticipated Questions and Your Responses
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15